## Azure Post-Migration Tuning
Area | Task | Description | Owner | Status | Remarks
Statistics & Indexes | Update Statistics | Update all table statistics immediately after migration
Statistics & Indexes | Rebuild Indexes | Fix fragmentation caused during migration
Statistics & Indexes | Enable Query Store | Enable Query Store & automatic tuning for regression handling
Database Settings | Check Compatibility Level | Ensure correct CE & version compatibility after migration
Performance Metrics | Review CPU Usage | Monitor CPU usage for performance spikes
Performance Metrics | Check IO Throughput | Review file IOPS & throughput on Azure storage
Performance Metrics | Monitor TempDB Usage | Check tempdb contention and spills
Query Optimization | Identify Slow Queries | Use Query Store & QPI to locate slow queries
Query Optimization | Fix Parameter Sniffing Issues | Review queries impacted after migration
Query Optimization | Review Missing Indexes | Identify & create necessary indexes from missing index DMV
Resource Sizing | Validate DTU/vCore Sizing | Ensure correct service tier after cutover
Networking | Check Network Latency | Validate connection latency & endpoints
Networking | Review Connection Strings | Ensure app uses correct retry logic & TLS settings
Automatic Tuning | Validate Auto Tuning Options | Check FORCE_LAST_GOOD_PLAN, CREATE/DROP INDEX options
Maintenance Jobs | Verify Maintenance Plans | Ensure index/statistics/DBCC jobs exist & run OK
Storage | Check Auto-growth Settings | Validate autogrowth for data, log & tempdb
Security | Review Encryption Impact | Ensure TDE/Always Encrypted do not cause performance issues