## Cloud Migration Risks
Risk ID | Category | Risk Description | Impact | Mitigation
R1 | Assessment & Planning | Incomplete application & dependency mapping | Migration failure or post-cutover issues | Perform full discovery using DMA, Network & Application mapping
R2 | Assessment & Planning | Wrong Azure service selection | Missing features or costly rework | Evaluate DB features; choose MI for full compatibility
R3 | Assessment & Planning | Incorrect sizing of CPU/IOPS | Slow performance, cost overruns | Use Azure Advisor + on-prem perf metrics
R4 | Technical Migration | Unsupported SQL features (CLR, linked servers) | Migration block or feature loss | Fix/replace unsupported objects before migration
R5 | Technical Migration | Bacpac/data migration failures | Incomplete migration | Use DMS for large DBs; avoid bacpac > 200GB
R6 | Technical Migration | Data loss or inconsistency | Incorrect data in production | Validate row counts, checksums, foreign keys
R7 | Technical Migration | Cutover failure/delta sync issue | Extended downtime | Plan rollback; ensure replication sync is clean
R8 | Performance | Cloud I/O performance mismatch | Slow queries | Choose appropriate tier; enable Query Store
R9 | Performance | Network latency issues | Application slowness | Use ExpressRoute/VPN + private endpoints
R10 | Security | Authentication failures (AD/AAD mismatch) | Users cannot connect | Convert logins → contained users; configure AAD
R11 | Security | Firewall/VNet misconfigurations | DB inaccessible | Configure NSG, VNet rules, private endpoints
R12 | Security | Encryption problems (TDE, Always Encrypted) | Data inaccessible or insecure | Migrate certificates; validate key vault
R13 | Operational | Missing DR strategy | No business continuity | Configure geo-replication + PITR policies
R14 | Operational | Missing monitoring & alerting | Outages or undetected issues | Enable Log Analytics + Alerts
R15 | Cost | Unexpected Azure cost overruns | Budget issues | Enable cost alerts, reserved instances, hybrid benefit
R16 | Rollback | No rollback plan | Production outage if migration fails | Maintain sync with on-prem; define rollback steps